## Test Summary
Test Summary Report - Google Translate Application As at 2024/04/29
Project Information: (Name) | The online product ‘Google Translate’
Test Objective | The purpose of testing Google Translator is to ensure the accuracy of the translations of English text to Sinhala and vice versa in different usage contexts
Version
Test Environment: | Browsers Executed(Chrome, Edge)
Test Execution time line 1 st round testing | 2024/04/27 to 2024/4/28
RTM Mapping Counts
Testing Techniques | Boundary Value Analysis Error Guessing
Covered Testing Types | Functional Testing | Smoke testing | Intergartion testing | Adhoc Testing | GUI testing | Positive testing | Negative testing | System testing | Regression testing
|  | Executed | Executed | Executed | Executed | Executed | Executed | Executed | Not executed
| Non Functional Testing | Browser Testing
Executed
| Performance testing | Load testing
Not executed
| Automation Testing | Automation Script - Not started
Not executed
Test cases Summary | Number of Total Test cases | 73
| Number of Total Executed Test cases | 71
| Number of Total Not Executed Test cases | 2
| Number of Total Passed Test cases | 65
| Number of Total fail Test cases | 6
| Number of Total Major Test cases | 50
| Number of Total Medium Test cases | 23
| Number of Total Minor Test cases | 0
| Number of Total Invalid test Cases | 0
| Number Of Total "Deferred" Test cases | 0
| Test coverage achieved | Number of tests executed*100 / Number of tests planned to be executed' 97.26%
Bugs Summery | Number of Total Bugs | 6
| Number of Critical Bugs | 0
| Number of Major Bugs | 2
| Number of Medium Bugs | 4
| Number of Minor Bugs | 0
| Number Of invlaid Bugs | 0
| Number Of Total "Deferred" Bugs | 0
Appendices |  | Detailed Bug report
Blockers
Dependancies